## Sheet1
|  | Completion % | [7 empty] | Complete by | #days Needed |  |  |  | Time Needed
Overall | Login functionality | 90% | [7 empty] | 2019-10-09 | 0
Overall | Web Page Design | 50% | [7 empty] | 2019-10-14 | 3 |  |  |  | < week
Overall Header Part 1 | Customer name, industry drop down, CARR typedrop down, currency, automated pupulating fields: Initiated By, Initiated On, Last Updated By, Last Updated On | [8 empty] | 2019-10-16 | 2 |  |  |  | < week
|  | Completion % |  | Completion % |  | Completion %
|  | DB design | Hours | Web Page User Interface | Hours | Biz Logic | Hours | DB design | Web Page User Interface | Biz Logic | #days @ 80% | #hours (80% of 7.5/day = 6 h) | Add-l resource a 3rd of the hours | Michele
per tab | Contract Info | 90% |  | 20% |  | 5% |  | 2019-10-18 | 2019-10-18 | 2019-10-22 | 4 | 24 | 8 | 16 | < week
per tab | Shipping Profile | 80% |  | 10% |  | 0% |  | 2019-11-01 | 2019-11-01 | 2019-10-28 | 0 | 0 | 0 | 0
per tab | sub tab 1 location | 80% |  | 10% |  | 0% |  | 2019-11-01 | 2019-11-01 | 2019-10-28 | 5 | 30 | 10 | 20 | 1 week
| sub tab 2 services | 80% |  | 10% |  | 0% |  | 2019-11-01 | 2019-11-01 | 2019-11-04 | 5 | 30 | 10 | 20 | 1 week
| sub tab 3 weekly revenue | 80% |  | 10% |  | 0% |  | 2019-11-01 | 2019-11-01 | 2019-11-11 | 2 | 12 | 4 | 8 | < week
Header 2 Done Next, before remaining tabs | Pricing Req vs Account Creation, Chain of approval & routing rules, Time Stamping, Version Creation, Ownership Display, Submit Button, Pricing Completed Check Box | [8 empty] | 2019-11-18 | 5 | 30 | 10 | 20 | 1 week
per tab | Brokerage |  |  |  |  | 0% |  |  |  | 2019-11-25 | 5 | 30 | 10 | 20 | 1 week
per tab | Exceptions |  |  |  |  | 0% |  |  |  | 2019-12-09 | 10 | 60 | 20 | 40 | 2 weeks | <= | Gray
per tab | Requests form |  |  |  |  | 0% |  |  |  | 2019-12-30 | 15 | 90 | 30 | 60 | 3 weeks |  | shaded
per tab | File uploads |  |  |  |  | 0% |  |  |  | 2020-01-06 | 5 | 30 | 10 | 20 | 1 week |  | cells
per tab | Notes |  |  |  |  | 0% |  |  |  | 2020-01-13 | 5 | 30 | 10 | 20 | 1 week |  | are
per tab | Account Creation |  |  |  |  | 0% |  |  |  | 2020-01-20 | 5 | 30 | 10 | 20 | 1 week |  | calcuated
On Shipping Profile | Service Specific Info | [8 empty] | 2020-01-23 | 3 | 18 | 6 | 12 | < week |  | dates
On Shipping Profile | Accessorials functionality | [8 empty] | 2020-02-13 | 15 | 90 | 30 | 60 | 3 weeks |  | based
On Shipping Profile | Billing Information | [8 empty] | 2020-02-27 | 10 | 60 | 20 | 40 | 2 weeks |  | on
On Shipping Profile | Returns | [8 empty] | 2020-03-05 | 5 | 30 | 10 | 20 | 1 week |  | # days
| Pricing functionality - to generate rates & CAVY functionality (for new & renewal); 33 to 6 zone conversion tool; | [8 empty] | 2020-03-26 | 15 | 90 | 30 | 60 | 3 weeks
| Adendums: format, logo, data entry fields & populating these fields | [8 empty] | 2020-04-09 | 10 | 60 | 20 | 40 | 2 weeks
| Excel Output (for rates) | [8 empty] | 2020-04-23 | 10 | 60 | 20 | 40 | 2 weeks
| PDF Output | [8 empty] | 2020-05-14 | 15 | 90 | 30 | 60 | 3 weeks
| Upload non editable attachments | [8 empty] | 2020-05-19 | 3 | 18 | 6 | 12 | < week
[10 empty] | TOTALS | 157 | 912 | 304 | 608
[10 empty] | Days | 157 |  |  | 101.3333
[10 empty] | Due date | 2020-05-19 |  |  | 2020-03-02
[10 empty] | Reduced days to completion due to add-l resoucre |  |  |  | -55.6667
Formulas:
Complete by = WORKDAY([Complete by, row above],L3)